## PPGPL
No. | Project Number | Project Name | UNSPSC Code Lvl 3 | Brief Description | Proposed date for Issue of Bidding Docs | Expected Delivery/ Completion date | Estimated Project Duration in days (for works and services) | Procurement Method | Standstill period (if applicable) - No. of days | Contract Type
1 | TBD | Facility Maintenance Campaign Q2 - Storage & Docks | Oil and gas engineering - 83101900 | Maintenance work originating from recommendations made during RBI inspections, visual inspections, and electrical inspections | 2025-05-25 | 2025-09-25 | 21 days | Tender | 10 | Service Contract
2 | TBD | Dock 1 Loading Line Refurbishment and Piping Repairs | Oil and gas engineering - 83101900 | External remediation of the remaining 50% of the Dock 1 loading line. | 2025-03-16 | 2025-07-16 | 40 days | Tender | 10 | Service Contract
3 | TBD | Dock 2 Loading Line Fabric Maintenance (MOV to Security Office) | Oil and gas engineering - 83101900 | Dock 2 Skid and Piping to storage fabric maintenance work. | 2025-02-16 | 2025-06-16 | 20 days | Tender | 10 | Service Contract
4 | TBD | Dock 1 & 2 Marine Bollard Testing | Oil and gas engineering - 83101900 | Gather and review all relevant data to aid with the inspection, testing and certification of all marine bollards on both Docks 1&2 | 2025-01-02 | 2025-05-02 | 20 days | Tender | 10 | Service Contract
5 | TBD | Repairs to T-101 | Oil and gas engineering - 83101900 | Repairs resulting from Fitness for Service assessment of the tower. | 2025-04-08 | 2025-08-08 | 20 days | Tender | 10 | Service Contract
6 | TBD | Repairs/Preservation of Isobutane Fan Bank | Oil and gas engineering - 83101900 | Perform repairs to loose plenum and structural members to reinforce them / secure all parts and maintain a safe area. | 2024-12-23 | 2025-04-23 | 20 days | RFQ | N/A | Service Contract
7 | TBD | PBC Dehydrators Molecular Sieve Changeout & Skid Repairs | Oil and gas engineering - 83101900 | Unloading of spent molecular sieve within the PBC Dehydrators, allow time for completion of internal inspections and repairs and re-load new sieve and box up vessels. | 2024-10-13 | 2025-02-13 | 21 days | Tender | 10 | Service Contract
8 | TBD | PK-5631 Generator Repairs - Generator Rental | Oil and gas engineering - 83101900 | Rental of a backup supply generator to support emergency requirements while the installed is being serviced/ repaired. | 2025-02-10 | 2025-06-10 | 35 days | RFQ | N/A | Service Contract
9 | TBD | PK-5631 Generator Repairs | Oil and gas engineering - 83101900 | Conduct Fuel Polishing, replace fuel tank and install new vibration isolators. | 2025-02-10 | 2025-06-10 | 35 days | RFQ | N/A | Service Contract
10 | TBD | Preservation of Frac 3 Refrigeration system | Industrial Refrigeration system - 24131500 | This project seeks to isolate, de-pressure, drain, purge, open/ disassemble, inspect, repair/reinstate, preserve with nitrogen or inert atmosphere all the main and auxiliary equipment associated with the Frac 3 refrigeration system loop. | 2025-03-16 | 2025-07-16 | 40 days | Tender | 10 | Service Contract
11 | TBD | Valve Maintenance - I&E | Valves - 40141600 | Major overhauls of valves, both control and shutdown and larger manual double block and bleed valves in 2025. | 2025-08-12 | 2025-12-12 | 365 days | RFQ | N/A | Service Contract
12 | TBD | Motor Maintenance | Motor installation and maintenance service - 72154302 | Major overhauls of motors for preventive and corrective maintenance in 2024. | 2025-08-12 | 2025-12-12 | 365 days | RFQ | N/A | Service Contract
13 | TBD | Plant Lighting and Facility Maintenance | Lighting system maintenance or repair service - 72151511 | Annual Plant Lighting repairs and Maintenance | 2025-08-19 | 2025-12-19 | 151 days | RFQ | N/A | Service Contract
14 | TBD | ALNG Prover Inspection, Upgrade and Re-certification | Oil and gas engineering - 83101900 | Inspection to assess the overall integrity and functionality of the installation. Allows for vendor recommendations to be provided for maintenance repairs, upgrades as well as recertification. | 2025-04-11 | 2025-08-11 | 45 days | RFQ | N/A | Service Contract
15 | TBD | Electrical Fabric Maintenance | Substation load control switchgears - 26131808 | Electrical repairs and maintenance on switchgears and transformers | 2025-08-17 | 2025-12-17 | 365 days | RFQ | N/A | Service Contract
16 | TBD | Facility Electrical Testing | Oil and gas engineering - 83101900 | Electrical testing of equipment throughout the facility | 2024-11-26 | 2025-03-26 | 181 days | RFQ | N/A | Service Contract
17 | TBD | Repairs to C-4451 Refrigerant Compressor | Oil and gas engineering - 83101900 | Possible repairs may include: • Impeller replacements. • Balance piston replacement. • Shaft replacement. • Labyrinth seals replacement. | 2025-06-16 | 2025-10-16 | 40 days | RFQ | N/A | Service Contract
18 | TBD | Condenser Fan Repairs | Oil and gas engineering - 83101900 | Repairs on the plenum areas, shrouds, guards and any other associated structural components of the condenser fans | 2024-12-04 | 2025-04-04 | 145 days | RFQ | N/A | Service Contract
19 | TBD | Refurbishment of Dock Ladders and Structures | Oil and gas engineering - 83101900 | Repairs identified for the refurbishment of the Dock 1 and Dock 2 ladders and infrastructure due to corrosion issues on platforms and supports and damage suffered due to tug and vessel impacts as well as environmental impact. | 2025-03-04 | 2025-07-04 | 80 days | RFQ | N/A | Service Contract
20 | TBD | Firewater Engines Inspections and Repairs | Fire prevention - 46191500 | Performance of inspections and repairs due to the continuous effects of the seawater service on the engines, pump internals and associated equipment. | 2025-08-02 | 2025-12-02 | 365 days | RFQ | N/A | Service Contract
21 | TBD | Fractionation 3 TAR Opportunity Works | Equipment inspection and verification services - 81141512 | Maintenance work originating from recommendations made during RBI inspections, visual inspections, and electrical inspections | 2025-05-09 | 2025-09-09 | 3 mons | RFQ, Tender | 10 | Service Contract
22 | TBD | Facility Maintenance - Road Paving/ Restoration/Concrete/ Blue Metal Reinstatement | Oil and gas engineering - 83101900 | Perform paving repairs to the roadway at the RTW loading station and surrounding all 3 gas plants and fractionating units basis civil challenges with drainage in this area. | 2025-08-12 | 2025-12-12 | 231 days | RFQ | N/A | Service Contract
23 | TBD | Statutory Inspections - Overhead Cranes | Lifting equipment and accessories - 24101600 | Statutory equipment Inspection and recertification. Required annually. | 2025-05-23 | 2025-09-23 | 10 days | RFQ | N/A | Service Contract
24 | TBD | Statutory Inspections - Relieving Devices | Valves - 40141600 | Statutory equipment Inspection and recertification. Required annually. | 2025-08-01 | 2025-12-01 | 92 days | Tender | 10 | Service Contract
25 | TBD | Statutory Inspections - Portable lifting devices, Slings, Safety Harnesses, In house lifting devices, hoses | Lifting equipment and accessories - 24101600 | Statutory equipment Inspection and recertification. Required annually. | 2025-03-08 | 2025-07-08 | 20 days | RFQ | N/A | Service Contract
26 | TBD | Statutory Inspections - Air receivers | Oil and gas engineering - 83101900 | Statutory equipment Inspection and recertification. Required annually. | 2025-04-11 | 2025-08-11 | 20 days | RFQ | N/A | Service Contract
27 | TBD | Statutory Inspections - LPG Interface Tanks | Storage Vessels and tanks - 20142900 | Statutory equipment Inspection and recertification. Required annually. | 2025-01-28 | 2025-05-28 | 15 days | RFQ | N/A | Service Contract
28 | TBD | Pipeline Marker Pole Refurbishment | Oil and gas engineering - 83101900 | Repair/ Replacement of marker posts and aerial markers due to corrosion. | 2025-02-05 | 2025-06-05 | 8 days | RFQ | N/A | Service Contract
29 | TBD | 8” NGL Pipeline Corrosion Growth Excavations | Oil and gas engineering - 83101900 | Supply of equipment and personnel to conduct excavations and inspections of selected areas of the 54 km long PPGPL 8” pipeline basis intelligent pigging findings. | 2025-02-01 | 2025-06-01 | 92 days | Tender | 10 | Service Contract
30 | TBD | Structural Integrity Baseline Assessment of Plant Infrastructure | Oil and gas engineering - 83101900 | Enhancement of Inspection data for structures throughout PPGPL’s Facility for baselining and repairs. | 2025-08-12 | 2025-12-12 | 365 days | Tender | 10 | Service Contract
31 | TBD | Integrity Assessment of the Fire Water Piping Ring | Fire prevention - 46191500 | Full assessment of all fire water piping inclusive of all above and below ground sections | 2025-08-12 | 2025-12-12 | 183 days | RFQ | N/A | Service Contract
32 | TBD | B-Vapour Recovery Unit Repairs/ Refurbishment | Oil and gas engineering - 83101900 | Insulation removal for inspections and subsequent reinstatement as well as vessel repairs. | 2024-11-20 | 2025-03-20 | 5 days | Tender | 10 | Service Contract
33 | TBD | Atlantic Skid | Oil and gas engineering - 83101900 | Fabric Maintenance works on Atlantic Skid at PPGPL and at Atlantic basis maintenance requirements. | 2025-06-01 | 2025-10-01 | 15 days | RFQ | N/A | Service Contract
34 | TBD | Insulation replacement throughout facility | Oil and gas engineering - 83101900 | Insulation reinstatement following completed inspections. | 2025-01-05 | 2025-05-05 | 20 days | Tender | 10 | Service Contract
35 | TBD | Product sample laboratory testing | Quality control - 81141506 | Contract Renewal - Full Medical Analysis Testing | 2025-06-01 | 2025-10-01 | 183 days | RFQ | N/A | Service Contract
36 | TBD | Laboratory equipment servicing | Laboratory equipment maintenance - 81101706 | Provision of remedial services to laboratory equipment | 2025-08-31 | 2025-12-31 | 365 days | RFQ | N/A | Service Contract
37 | TBD | Export of product samples for lab testing | Freight forwarders services - 78141501 | To provide shipping, sample handling and documentation | 2025-03-01 | 2025-07-01 | 183 days | RFQ | N/A | Service Contract
38 | TBD | Analyzer equipment repairs | Laboratory equipment maintenance - 81101706 | Equipment Repairs | 2026-02-01 | 2026-06-01 | 365 days | RFQ | N/A | Service Contract
39 | TBD | Equipment calibration service | Laboratory equipment maintenance - 81101706 | Calibrations | 2026-03-01 | 2026-07-01 | 365 days | RFQ | N/A | Service Contract
40 | TBD | Analyzer equipment calibration service | Laboratory equipment maintenance - 81101706 | Calibrations | 2025-09-01 | 2026-01-01 | 365 days | RFQ | N/A | Service Contract
41 | TBD | Training on Self Contained Breathing Apparatus | Labor training or development - 80111504 | Training on SCBAs | 2024-10-01 | 2025-02-01 | 31 day | RFQ | N/A | Service Contract
42 | TBD | Indoor Air Quality Monitoring | Air pollution - 77121500 | Execution of environmental testing to determine the level of contaminants present in the indoor air that can affect the well-being of the building occupants as well as their productivity. | 2024-11-01 | 2025-03-01 | 30 days | RFQ | N/A | Service Contract
43 | TBD | Fire hoses & carts inspection | Fire prevention - 46191500 | Quarterly Inspection of ten (10) Fire Hose Reels (located at the Plant and Corporate Office - Rivulet Road) and two (2) Plant Fire Carts c/w four (4) Lay Flat Fire Hoses. | 2024-10-01 | 2025-02-01 | 31 days | RFQ | N/A | Service Contract
44 | TBD | Service of Fire Alarm systems | Fire prevention - 46191500 | To conduct (bi-annual) servicing of the Fire Alarm system at Admin Building. | 2025-03-01 | 2025-07-01 | 5 days | RFQ | N/A | Service Contract
45 | TBD | Fire suppression/fire detection - Records Center & Engineering Doc. Room | Fire prevention - 46191500 | To conduct quarterly service and maintenance of the Fike fire detection & fire suppression system in the Records Center & Engineering Document Room. | 2024-10-01 | 2025-02-01 | 5 days | RFQ | N/A | Service Contract
46 | TBD | Fixed Gas Cloud Imaging Cameras for Detection and GHG Monitoring | Environmental monitoring - 77101505 | Installation of specialised camera with the ability to detect gas leaks/releases that are invisible to the human eye. These gases can lead to safety hazards, environmental damage and economic losses. | 2025-08-01 | 2025-12-01 | 213 days | Tender | 10 | Service Contract
47 | TBD | Climate Risk Assessment | Air pollution - 77121500 | Execution of a study to identify the likelihood of future hazards that can impact PPGPL’s operations associated with changes in climatic conditions. | 2025-01-01 | 2025-05-01 | 31 days | RFQ | N/A | Service Contract
48 | TBD | ESG Rating | Air pollution - 77121500 | Establishment of a rating on environmental, social and governance parameters of PPGPL’s operations that can provide an indication of PPGPL’s sustainability performance. The rating is conducted by an independent party. | 2024-12-01 | 2025-04-01 | 120 days | RFQ | N/A | Service Contract
49 | TBD | Complete a Double Materiality Assessment | Environmental Impact Assessment EIA services - 77101504 | Execution of an analysis of the impact of sustainability related factors, such as extreme weather events and government policies, on PPGPL’s business as well as the impact of PPGPL’s operations on the surrounding environment. The analysis is conducted by an independent party. | 2025-01-01 | 2025-05-01 | 120 days | RFQ | N/A | Service Contract
50 | TBD | Traction Guest Hardware Upgrade | Computer accessories - 43211613 | Hardware upgrade | 2025-03-01 | 2025-07-01 | 92 days | RFQ | N/A | Service Contract
51 | TBD | DCS & SIS Upgrade | Process control or packaged automation systems - 32152000 | To upgrade the exisitng Honeywell DCS & SIS install based to address obsolescene issues | 2028-07-09 | 2028-11-09 | 1758 days | Tender | 10 | Service Contract
52 | TBD | Dock Transfer Operations Project - Single Dock Operation | Building and Facility Construction and Maintenance Services - 72101507 | The Dock Transfer Operations Project - Single Dock Operation aims to address the reliability and maintenance issues identified for a single dock operation by installing an additional loading arm and loading line on Dock 2. In addition, the scope includes the relocation of the SW/FW pumps, currently at Dock 1 to Dock 2. | 2028-03-03 | 2028-07-03 | 1654 days | Tender | 10 | Service Contract
53 | TBD | Emergency Shut Down (ESD) Philosophy Project | Feasibility studies or screening of project ideas - 80101601 | To review the feasibility of segregating the shutdown of the facility based on the current initiating events that activate the present Facility ESD. To rationalize the existing 41 ESD buttons on the Facility (determining the requirement and function of each ESD button), and ensure that “safe” operations is maintained and no new risks are introduced. To ensure that the functionality of the FSC as a Layer of Protection for the Facility is not compromised due to any revision of the ESD Philosophy | 2024-12-25 | 2025-04-25 | 360 days | Tender | 10 | Service Contract
54 | TBD | New Fire suppression System in Control Room IO Building | Fire prevention - 46191500 | Control IO & server rooms needs to be outfitted with a suppression system to activate in the event of a fire as it houses critical devices which is essential for operating the facility. | 2026-08-28 | 2026-12-28 | 689 days | Tender | 10 | Service Contract
55 | TBD | Gasoline Segregation Project | Pipefitting fabrication and maintenance services - 72154401 | The Gasoline Segregation Project will install approximately 1200ft of 4inch Piping which will allow Gasoline produced from Fractionation 3 to be stored separately from Gasoline produced from Fractionation 2. Existing tie-in are being utilized for this project. The Stage 2 TIC is USD $ 741. | 2025-10-03 | 2026-02-03 | 224 days | Tender | 10 | Service Contract
56 | TBD | Heaters Upgrade (H-201 & H501) | Oil and gas engineering - 83101900 | To upgrade the H-201 and H501 Regeneration Gas Heater to address safety, code compliance, and obsolescence risk | 2028-08-27 | 2028-12-27 | 1969 days | Tender | 10 | Service Contract
57 | TBD | Heater Integration Project | Oil and gas engineering - 83101900 | The Heater integration Project Presents an oppertunity to determin a suitable engineering solution to integrate the hot oil circulation loop to maximise the excess duty capacity for each heater. | 2026-06-26 | 2026-10-26 | 1491 days | Tender | 10 | Service Contract
58 | TBD | New Air Compressor | Compressors - 40151600 | Addition of another high capacity 365 SCFM unit is necessary to ensure that redundancy exists in the Instrument Air compressor supply system, in the event of a loss of the existing high capacity unit or one or more of the lower capacity units | 2026-11-11 | 2027-03-11 | 1724 days | Tender | 10 | Service Contract
59 | TBD | Replacement of Overhead lines and Conductors | Electrical cable and accessories - 26121600 | Improvement of the robustness of the 12KV power distribution to the facility which at the same time will mitigate risk to nearby equipment and address the integrity, maintenance and operational/safety issues which the current infrastructure poses. |  |  | 3703 days | Tender | 10 | Service Contract
60 | TBD | Transformer Fire & Explosion Protection Scheme for the Main Substation, Fractionation 1,2 & 3 | Fire prevention - 46191500 | To implement a fire and explosion protection scheme for the Main Substation | 2031-04-01 | 2031-08-01 | 2571 days | Tender | 10 | Service Contract
61 | TBD | Truck Loading Station Upgrade | Oil and gas utilities - 83101600 | To mitigate the potential risks to safe and reliable truck loading operations due to code compliance related issues of the existing truck loading infrastructure and to manage LPG supply to the country during normal operations and during a FTAR independently. | 2024-09-06 | 2025-01-06 | 768 days | Tender | 10 | Service Contract
62 | TBD | New Loading Arm Dock 1 Project | Marine loading arm - 40142600 | New PPGPL Dock 1 LPG Loading Arm EPC. | 2026-05-23 | 2026-09-23 | 932 days | Tender | 10 | Service Contract
63 | TBD | Butane Supply to the Nation - Phase 1 | Pipefitting fabrication and maintenance services - 72154401 | For the LPG products (Propane and Butane), PPGPL currently utilizes the existing TLS for the loading of Propane into Road Tanker Wagons (RTW) for supply to the local market. For the Butane product, PPGPL currently utilizes pipelines routed from PPGPL to Aerogas, where RTWs are loaded with Butane for supply to the local market. The loading of Propane at PPGPL and Butane at Aerogas cannot occur simultaneously. To enable simultaneous Propane and Butane RTW loadings, modifications to the PPGPL plant infrastructure is required. | 2025-02-26 | 2025-06-26 | 362 days | Tender | 10 | Service Contract
64 | TBD | Pump - P705 | Pipefitting fabrication and maintenance services - 72154401 | Installation and Commission to Pump. | 2025-04-21 | 2025-08-21 | 291 days | Tender | 10 | Service Contract
65 | TBD | Dock 1 Transfer Operations | Pipefitting fabrication and maintenance services - 72154401 | An assessment of the transfer of PPGPL’s Dock 1 operations to its Dock 2 facility is required to mitigate against the risk of PPGPL losing its marketing flexibility and effective emergency fire response in the event where Yara ceases renewal of the agreement or proposes unfavorable terms and conditions. | 2024-12-22 | 2025-04-22 | 868 days | Tender | 10 | Service Contract
66 | TBD | Dock 2 Shoreline Remediation and Protection | Marine construction services - 72141200 | Dock 2 Shoreline restoration project - protection of Dock 2 southern shoreline from coastal erosion with an Armour Rock revetment structure | 2026-03-17 | 2026-07-17 | 1406 das | Tender | 10 | Service Contract
67 | TBD | Shelter In Place project Engineering Procurement & Construction strategy | Onshore engineering procurement and construction services - 81103400 | Currently There are a total of five shelter In Place (SIP) location at the plant facility and the marine terminal. The intent of these SIPs is to provide an indoor safe location as temporary occupancy in the event of a toxic release event which can potentially impact personnel locatedon the PPGgPL facility | 2026-03-03 | 2026-07-03 | 597 days | Tender | 10 | Service Contract
68 | TBD | Firewall Consultancy Support | Security and protection software maintenance - 81112208 | Services to augment internal resources for internal firewalls technical support. Troubleshooting, Breakfix, Reconfigurations, deployments | 2025-01-01 | 2025-12-01 | 480 days | RFP | 10 | Service Contract
69 | TBD | Software Infrastructure Support Services 1 | Software maintenance and support - 81112200 | Services to augment internal resources for specific microsoft systems technical support. Troubleshooting, Breakfix, Reconfigurations, deployments | 2025-01-01 | 2025-12-01 | 480 days | Tender | 10 | Service Contract
70 | TBD | Network Infrastructure Support Services | Network application software maintenance - 81112218 | Services to augment internal resources for Network services. Troubleshooting, Breakfix, Reconfigurations, deployments | 2025-06-01 | 2025-12-01 | 480 days | RFP | 10 | Service Contract
71 | TBD | Oracle OCI Support Services | Software maintenance and support - 81112200 ERP or database applications programming services - 81111507 | Services to augment internal resources for OCI services. Troubleshooting, Breakfix, Reconfigurations, deployments | 2025-06-01 | 2025-12-01 | 480 days | RFP | 10 | Service Contract
72 | TBD | Help Desk Support Services | Technical support or help desk services - 81111811 | Services to augment internal resources for Help Desk Support | 2025-02-01 | 2025-12-01 | 480 days | RFP | 10 | Service Contract
73 | TBD | Conference Room equipment maintenance | Video conferencing software maintenance - 81112207; Software maintenance and support - 81112200 | Services to augment internal resources for meeting room maintenance. Troubleshooting, Breakfix, Reconfigurations, deployments | 2025-04-01 | 2025-12-01 | 480 days | RFP | 10 | Service Contract
74 | TBD | Oracle E-Business Support | ERP or database applications programming services - 81111507 | Services to augment internal resources for specific Oracle Ebusiness Suite. Troubleshooting, Breakfix, Reconfigurations | 2025-02-01 | 2025-12-01 | 720 days | Tender | 10 | Service Contract
75 | TBD | Azure CSP Credits | Computer software licensing service - 81112501 | Azure credit purchase | 2025-01-01 | 2025-06-01 | 240 days | Tender | 10 | Purchase Order
76 | TBD | OCI Credits | Computer software licensing service - 81112501; Propietary or licensed systems maintenance or support - 81111805 | Oracle OCI credits purchase | 2025-03-01 | 2025-06-01 | 240 days | RFP | 10 | Purchase Order
77 | TBD | Software Licenses renewals | Computer software licensing service - 81112501 | Microsoft software subscription renewals | 2025-04-01 | 2025-06-01 | 240 days | RFP | 10 | Purchase Order
78 | TBD | System administration support services | System management software maintenance - 81112210; System or application programming management service - 81111511; | Services to augment internal resources for system administration. General sysadministration of IT systems | 2025-03-01 | 2025-12-01 | 240 days | RFP | 10 | Service Contract
79 | TBD | Backup Software | Security and protection software maintenance - 81112208 | Backup software subscription renewal | 2025-07-01 | 2025-12-01 | 240 days | RFP | 10 | Purchase Order
80 | TBD | Firewall Software | Security and protection software maintenance - 81112208 | Various firewall software to be purchased | 2025-03-01 | 2025-12-01 | 240 days | RFP | 10 | Purchase Order
82 | TBD | Obsolete Computer Disposal | Refuse collection and disposal - 76121500 | Environmental disposal of Computer assets | 2025-09-01 | 2025-12-01 | 240 days | RFP | 10 | Service Contract
83 | TBD | Computer Hardware | Computer or network or internet security - 81111801; Computer hardware maintenance and support - 81112300 | Computers, Servers, Network Switches, Wireless Access Points, Monitors and Laptops | 2025-02-01 | 2025-12-01 | 240 days | RFP | 10 | Purchase Order
86 | TBD | Uninterruptable Power Supplies | Uninterruptible power supply UPS - 39121011 | Uninterruptable Power Supplies | 2025-02-01 | 2025-12-01 | 240 days | RFP | 10 | Purchase Order
Formulas:
Proposed date for Issue of Bidding Docs = EDATE([Expected Delivery/ Completion date],-4)
Note on G62: Alson Bobcombe - TPMSL Contractor: Date covers the end of Stage 2 only